## Sheet1
Tasks | Expected Completion Date | Actual Completion Date | Status | Reason if Milestone Not Met, or Comments
Planning
Meet with Client | 2021-02-21 | 2021-02-21 | Complete
Gather Requirements | 2021-02-26 | 2021-02-26 | Complete
Create Use Cases | 2021-03-04 | 2021-03-04 | Complete
Create SPMP | 2021-03-04 | 2021-03-04 | Complete | Revised as project moved
Research
Research possible website hosts | 2021-03-05 | 2021-03-05 | Complete | Wordpress
Research necessary tools and APIs | 2021-03-05 | 2021-03-12 | Complete | S2Membership, Zillow
Research usable payment processors | 2021-03-12 | 2021-03-12 | Complete | Paypall
Review Budget | 2021-03-19 | 2021-03-19 | Complete
Design Review Meeting | 2021-03-31 | 2021-04-02 | Complete | After Deadline of 31st
Design and Implementation
Design front-end framework | 2021-04-20 | 2021-04-20 | Complete
Integrate site membership and set up DB | 2021-04-22 | 2021-04-22 | Complete
Successively integrate needed plug-ins and APIs | 2021-04-23 | 2021-04-23 | Complete
Test and Finalize Project
Test plug-ins function properly | 2021-04-24 | 2021-04-24 | Complete | Schedule Appointments, S2Member,
Test APIs function properly | 2021-04-24 | 2021-04-24 | In Progress | Change of plans, no longer using Google API
Test payment method for secure payments | 2021-04-25 | 2021-04-25 | Complete | PayPal
Make Revisions and Changes if necessary | 2021-04-26 |  | In Progress | Revisions still being made,
Test Changes | 2021-04-26 |  | In Progress | Changes not yet completed to test
Update Design Documents as needed | 2021-04-26 |  | In Progress | Design Documents and SPMP still up for possible updates